## Sheet1
Stream | Task | CISO/CIO | Sec Arch | IT Ops | Proc | Legal | BU/App | 3P/SC
Stream 1 - Governance & Accountability | Establish PQC program authority and assign executive owner | A/R | C | I | I | C | I | I
Stream 1 - Governance & Accountability | Define program scope and budget and phased timeline | A/R | C | C | C | C | I | I
Stream 1 - Governance & Accountability | Create escalation path and exception handling process | A/R | C | I | I | C | I | I
Stream 1 - Governance & Accountability | Establish cadence for milestone tracking and reporting | A | R | C | I | I | I | I
Stream 1 - Governance & Accountability | Select applicable frameworks (NIST CSF / ISO 27001 etc.) | A | R | C | I | C | I | I
Stream 1 - Governance & Accountability | Define crypto-agility as a program requirement | A | R | C | I | C | I | I
Stream 1 - Governance & Accountability | Assign stream owners and accountabilities | A/R | C | C | C | C | C | I
Stream 1 - Governance & Accountability | Establish vendor accountability requirements and procurement gates | A | C | I | R | C | I | C
Stream 2 - Inventory & Risk Assessment | Identify all systems using asymmetric cryptography | A | R | C | I | I | C | I
Stream 2 - Inventory & Risk Assessment | Inventory certificate authorities and HSMs and PKI infrastructure | A | R | C | I | I | I | I
Stream 2 - Inventory & Risk Assessment | Identify signing pipelines and code signing and firmware signing systems | A | R | C | I | I | C | I
Stream 2 - Inventory & Risk Assessment | Inventory IoT and OT and shopfloor systems using cryptography | A | C | R | I | I | C | I
Stream 2 - Inventory & Risk Assessment | Classify data by sensitivity and lifespan and quantum exposure | A | R | I | I | C | C | I
Stream 2 - Inventory & Risk Assessment | Identify third-party and supply chain cryptographic dependencies | A | R | I | C | C | C | R
Stream 2 - Inventory & Risk Assessment | Assess each system against Harvest Now Decrypt Later risk | A | R | C | I | I | C | I
Stream 2 - Inventory & Risk Assessment | Assign risk priority and migration urgency to each asset | A | R | C | I | C | C | I
Stream 2 - Inventory & Risk Assessment | Establish inventory as a living document with ownership | A | R | C | I | I | C | I
Stream 3 - Standards Adoption & Tracking | Adopt NIST FIPS 203 (ML-KEM) for key exchange | A | R | C | I | I | I | I
Stream 3 - Standards Adoption & Tracking | Adopt NIST FIPS 204 (ML-DSA) for general-purpose signing | A | R | C | I | I | I | I
Stream 3 - Standards Adoption & Tracking | Adopt NIST FIPS 205 (SLH-DSA) for high-assurance signing | A | R | C | I | I | I | I
Stream 3 - Standards Adoption & Tracking | Define approved hybrid key exchange policy (X25519 + ML-KEM) | A | R | C | I | C | I | I
Stream 3 - Standards Adoption & Tracking | Document industry-specific requirements (X9.146 / OMB M-26-15 / CNSA 2.0) | A | R | I | I | R | I | I
Stream 3 - Standards Adoption & Tracking | Define crypto-agility requirements for all new systems and procurements | A | R | C | R | C | I | C
Stream 3 - Standards Adoption & Tracking | Establish algorithm sunset and review cadence | A | R | I | I | C | I | I
Stream 3 - Standards Adoption & Tracking | Track NIST and IETF and NSA standards evolution | A | R | I | I | C | I | I
Stream 4 - Systems & Supply Chain Remediation | Assess each inventoried system against approved PQC standards | A | R | C | I | I | C | I
Stream 4 - Systems & Supply Chain Remediation | Assign migration path per system: in-place / re-platform / or retire | A | R | C | C | I | C | I
Stream 4 - Systems & Supply Chain Remediation | Update certificate authorities and PKI infrastructure for ML-DSA / SLH-DSA | A | R | R | I | I | I | C
Stream 4 - Systems & Supply Chain Remediation | Upgrade or replace HSMs for PQC key generation and storage | A | C | R | C | I | I | C
Stream 4 - Systems & Supply Chain Remediation | Update software and firmware signing pipelines | A | R | R | I | I | C | I
Stream 4 - Systems & Supply Chain Remediation | Define and enforce PQC requirements in vendor contracts | A | C | I | R | R | I | C
Stream 4 - Systems & Supply Chain Remediation | Obtain vendor roadmaps with committed PQC delivery dates | A | C | I | R | C | I | R
Stream 4 - Systems & Supply Chain Remediation | Assess and plan for IoT/OT systems with long replacement cycles | A | R | C | C | I | C | I
Stream 4 - Systems & Supply Chain Remediation | Document exceptions with compensating controls and sunset dates | A | R | C | I | C | C | I
Stream 4 - Systems & Supply Chain Remediation | Validate supply chain PQC readiness against defined requirements | A | R | I | R | C | C | R
Stream 5 - Infrastructure & Endpoint Migration | Deploy hybrid PQC key exchange at internet-facing TLS endpoints | A | C | R | I | I | I | I
Stream 5 - Infrastructure & Endpoint Migration | Deploy PQC to internal service-to-service communication and VPNs | A | C | R | I | I | C | I
Stream 5 - Infrastructure & Endpoint Migration | Migrate authentication systems and identity providers to PQC | A | R | R | I | I | C | I
Stream 5 - Infrastructure & Endpoint Migration | Update key management infrastructure for PQC-protected key exchange | A | R | R | C | I | I | I
Stream 5 - Infrastructure & Endpoint Migration | Migrate data-at-rest encryption for high-value and long-lifespan data | A | R | C | I | C | C | I
Stream 5 - Infrastructure & Endpoint Migration | Validate compatibility and performance of PQC deployments | A | C | R | I | I | C | I
Stream 5 - Infrastructure & Endpoint Migration | Test for packet fragmentation and handshake size issues across edge devices | A | C | R | I | I | I | I
Stream 5 - Infrastructure & Endpoint Migration | Track migration status against inventory — migrated / pending / excepted | A | R | C | I | I | C | I
Stream 5 - Infrastructure & Endpoint Migration | Confirm full deprecation of quantum-vulnerable solutions per asset | A | R | C | I | C | C | I
Stream 5 - Infrastructure & Endpoint Migration | Review and update crypto-agility configuration with each standards update | A | R | R | I | I | I | I